## Description
Requirements Prioritization Model
Karl Wiegers
This spreadsheet contains a simple model for estimating the relative priorities of implementing
specific features or requirements in a software system. The "Example" worksheet contains an
example, from a project called the Chemical Tracking System. The worksheet called
"Template" contains several blank rows that contain all the formulas. To use this tool, copy
the "Template" worksheet into a new spreadsheet file and enter your own items to be prioritized,
copying and inserting blank rows as necessary to get enough space to handle all the items you
wish to prioritize in one pass.
The priority is considered to be a function of how desirable it is to include a specific feature
(where desirability considers both the benefit the feature would provide to the customer, and
the penalty you might incur in the customer's eyes if the feature is omitted), and both the
relative cost and technical risk associated with implementing the feature. Every proposed feature
is rated for each of the four dimensions (benefit, penalty, cost, risk) on a relative scale
of 1-9 (9 is high). You can also adjust the weighting factors for each of these four dimensions. For example,
if you feel that benefit is twice as important as penalty, which is the same importance as cost,
but risk is only half as important as cost, then you would use weighting factors (in row 1 of the
example) of 2, 1, 1, and 0.5, respectively.
After entering the relative numbers for all the features, the relative priority for each
feature is calculated by considering the percentage of the weighted feature desirability
(or value), cost, and risk attributable to each feature. If you sort the list of features
descending by the "Priority" column, the top priority items are at the top of the list.
You would not use this approach to estimate priorities for features that you know must be included,
for any reason (political, competitive advantage, regulatory or contractual requirement, etc.). Only
use this tool as a way to differentiate among requirements that are not on the list of "absolutely
must do"s.
The "Multiple Stakeholders" worksheet illustrates a refinement of the basic spreadsheet that accommodates
multiple stakeholders or user classes who have different ideas about requirement priorities. This example
handles three stakeholders. Each stakeholder has a separate pair of columns for rating benefit and penalty.
The numbers in row 1 indicate the relative weight that each stakeholder gets in the decision-making process.
Favored user classes get higher weighting factors. The spreadsheet incorporates those weights when it
calculates the overall benefit and penalty numbers for each proposed requirement. You can experiment
with the benefit and penalty values, and the weighting factors, in this worksheet to see the effect of different
stakeholder evaluations on the calculated priority numbers.
This spreadsheet is Copyright © 2013 by Karl Wiegers and Seilevel.
Permission is granted to use, modify, and distribute this spreadsheet file.
More information about the model can be found in Software Requirements, 3rd Edition by Karl Wiegers and Joy Beatty,
Microsoft Press, 2013

## HMS
Relative Weights: | 1 | 1 |  |  | 1 |  | 1
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Check in | 9 | 9 | 18 | 8.4112 | 6 | 26.087 | 7 | 25.9259 | 0.16171
Check out | 9 | 9 | 18 | 8.4112 | 6 | 26.087 | 7 | 25.9259 | 0.16171
Make Bill | 5 | 4 | 9 | 4.2056 | 5 | 21.7391 | 5 | 18.5185 | 0.10447
View Available Room | 4 | 4 | 8 | 3.7383 | 1 | 4.3478 | 2 | 7.4074 | 0.31801
Search Room | 3 | 2 | 5 | 2.3364 | 2 | 8.6957 | 2 | 7.4074 | 0.14509
View Available Service | 3 | 3 | 6 | 2.8037 | 1 | 4.3478 | 2 | 7.4074 | 0.23851
Search Service | 3 | 2 | 5 | 2.3364 | 2 | 8.6957 | 2 | 7.4074 | 0.14509
View Check-in information | 6 | 5 | 11 | 5.1402 | 1 | 4.3478 | 3 | 11.1111 | 0.33251
Search Check-in information | 3 | 2 | 5 | 2.3364 | 2 | 8.6957 | 3 | 11.1111 | 0.11796
Edit Check-in information | 2 | 2 | 4 | 1.8692 | 2 | 8.6957 | 3 | 11.1111 | 0.09437
View Check-out information | 6 | 5 | 11 | 5.1402 | 1 | 4.3478 | 3 | 11.1111 | 0.33251
Search Check-out information | 3 | 2 | 5 | 2.3364 | 2 | 8.6957 | 3 | 11.1111 | 0.11796
Edit Check-out information | 2 | 2 | 4 | 1.8692 | 2 | 8.6957 | 3 | 11.1111 | 0.09437
Add New Room | 5 | 6 | 11 | 5.1402 | 3 | 13.0435 | 3 | 11.1111 | 0.2128
Delete a Room | 4 | 5 | 9 | 4.2056 | 2 | 8.6957 | 4 | 14.8148 | 0.17888
Edit a Room | 2 | 2 | 4 | 1.8692 | 2 | 8.6957 | 2 | 7.4074 | 0.11607
View Room List | 6 | 6 | 12 | 5.6075 | 1 | 4.3478 | 1 | 3.7037 | 0.69645
Add New Service | 5 | 6 | 11 | 5.1402 | 3 | 13.0435 | 3 | 11.1111 | 0.2128
Delete a Service | 4 | 5 | 9 | 4.2056 | 2 | 8.6957 | 4 | 14.8148 | 0.17888
Edit a Service | 2 | 2 | 4 | 1.8692 | 2 | 8.6957 | 2 | 7.4074 | 0.11607
View Service List | 6 | 6 | 12 | 5.6075 | 1 | 4.3478 | 1 | 3.7037 | 0.69645
Delete a Customer Information | 6 | 6 | 12 | 5.6075 | 1 | 4.3478 | 4 | 14.8148 | 0.29263
Edit a Customer Information | 7 | 6 | 13 | 6.0748 | 1 | 4.3478 | 3 | 11.1111 | 0.39296
View Customer Information | 4 | 4 | 8 | 3.7383 | 1 | 4.3478 | 4 | 14.8148 | 0.19508
Totals | 109 | 105 | 214 | 100 | 23 | 226.087 | 27 | 281.4815 | 5.6534

## Multiple Stakeholders
Relative Weights: | 3 |  | 1 |  | 1 |  | 1 | 1 |  |  | 1 |  | 1
| Receptionist |  | Develop Team |  | Manager
Feature | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Total Benefit | Total Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Check in | 9 | 3 | 4 | 7 | 2 | 3 | 6.6 | 3.8 | 10.4 | 5.5026 | 6 | 11.5385 | 7 | 9.2105 | 0.2652
Check out | 9 | 3 | 4 | 7 | 2 | 3 | 6.6 | 3.8 | 10.4 | 5.5026 | 6 | 11.5385 | 7 | 9.2105 | 0.2652
Make Bill | 8 | 3 | 6 | 6 | 2 | 3 | 6.4 | 3.6 | 10 | 5.291 | 5 | 9.6154 | 5 | 6.5789 | 0.32672
View Available Room | 8 | 3 | 6 | 4 | 7 | 3 | 7.4 | 3.2 | 10.6 | 5.6085 | 1 | 1.9231 | 2 | 2.6316 | 1.2314
Search Room | 6 | 3 | 3 | 1 | 5 | 3 | 5.2 | 2.6 | 7.8 | 4.127 | 2 | 3.8462 | 2 | 2.6316 | 0.6371
View Available Service | 8 | 3 | 6 | 4 | 7 | 3 | 7.4 | 3.2 | 10.6 | 5.6085 | 1 | 1.9231 | 2 | 2.6316 | 1.2314
Search Service | 6 | 3 | 3 | 1 | 5 | 3 | 5.2 | 2.6 | 7.8 | 4.127 | 2 | 3.8462 | 2 | 2.6316 | 0.6371
View Check-in information | 7 | 3 | 4 | 5 | 4 | 3 | 5.8 | 3.4 | 9.2 | 4.8677 | 1 | 1.9231 | 3 | 3.9474 | 0.82919
Search Check-in information | 4 | 3 | 2 | 1 | 3 | 3 | 3.4 | 2.6 | 6 | 3.1746 | 2 | 3.8462 | 3 | 3.9474 | 0.40734
Edit Check-in information | 5 | 3 | 2 | 2 | 3 | 3 | 4 | 2.8 | 6.8 | 3.5979 | 2 | 3.8462 | 3 | 3.9474 | 0.46165
View Check-out information | 7 | 3 | 4 | 5 | 2 | 3 | 5.4 | 3.4 | 8.8 | 4.6561 | 1 | 1.9231 | 3 | 3.9474 | 0.79314
Search Check-out information | 4 | 3 | 2 | 1 | 1 | 3 | 3 | 2.6 | 5.6 | 2.963 | 2 | 3.8462 | 3 | 3.9474 | 0.38018
Edit Check-out information | 5 | 3 | 2 | 2 | 1 | 3 | 3.6 | 2.8 | 6.4 | 3.3862 | 2 | 3.8462 | 3 | 3.9474 | 0.43449
Add New Room | 3 | 3 | 7 | 4 | 8 | 3 | 4.8 | 3.2 | 8 | 4.2328 | 3 | 5.7692 | 3 | 3.9474 | 0.43563
Delete a Room | 2 | 3 | 6 | 3 | 7 | 3 | 3.8 | 3 | 6.8 | 3.5979 | 2 | 3.8462 | 4 | 5.2632 | 0.39497
Edit a Room | 1 | 3 | 6 | 2 | 5 | 3 | 2.8 | 2.8 | 5.6 | 2.963 | 2 | 3.8462 | 2 | 2.6316 | 0.45741
View Room List | 2 | 3 | 5 | 4 | 8 | 3 | 3.8 | 3.2 | 7 | 3.7037 | 1 | 1.9231 | 1 | 1.3158 | 1.1435
Add New Service | 3 | 3 | 7 | 4 | 8 | 3 | 4.8 | 3.2 | 8 | 4.2328 | 3 | 5.7692 | 3 | 3.9474 | 0.43563
Delete a Service | 2 | 3 | 6 | 3 | 7 | 3 | 3.8 | 3 | 6.8 | 3.5979 | 2 | 3.8462 | 4 | 5.2632 | 0.39497
Edit a Service | 1 | 3 | 6 | 2 | 5 | 3 | 2.8 | 2.8 | 5.6 | 2.963 | 2 | 3.8462 | 2 | 2.6316 | 0.45741
View Service List | 2 | 3 | 5 | 4 | 8 | 3 | 3.8 | 3.2 | 7 | 3.7037 | 1 | 1.9231 | 1 | 1.3158 | 1.1435
Delete a Customer Information | 4 | 3 | 4 | 5 | 2 | 2 | 3.6 | 3.2 | 6.8 | 3.5979 | 1 | 1.9231 | 4 | 5.2632 | 0.50066
Edit a Customer Information | 5 | 3 | 5 | 2 | 2 | 2 | 4.4 | 2.6 | 7 | 3.7037 | 1 | 1.9231 | 3 | 3.9474 | 0.63091
View Customer Information | 7 | 3 | 5 | 7 | 5 | 3 | 6.2 | 3.8 | 10 | 5.291 | 1 | 1.9231 | 4 | 5.2632 | 0.73627
Totals | 118 | 72 | 110 | 86 | 109 | 70 | 114.6 | 74.4 | 189 | 100 | 52 | 100 | 76 | 100